## Product Roadmap
Agile Product Roadmap
<Agile Development Project> | Q2 |  |  | Q3 |  |  | Q4
| April | May | June | July | August | September | October | November | December
Group 1
Group 2
Group 3 | z
Group 4
Group 5
Create an Agile Product Roadmap in Smartsheet
Product 1
Online retailer
Product 3
Product 4
Product 5

## Project Charter
Agile Project Charter
General Project Information
Project Name | Online retailer Group 2
Project Champion | Bill Gate
Project Sponsor | Li Ka Shing
Project Manager | Liu Wai Man
Stakeholders | Lau Chun Hang, Ng Ka Ming, Poon Wai Lok, Fong Cheuk Lok
Expected Start Date | 1/24/2018
Expected Completion Date | 3/14/2018
Project Details
Mission | Contacting a customer > Producing a product > Transporting a product to a customer > Communicating with a customer
Vision | Making profit every year with the experienced service line to take the majority of the international market
Scope | Collecting and anlaysing customer requirements for product the high quality services
Success Metrics | The customer likes our product, the customer loyalty, produces the product in the budget and the scheduled time.
Date: | Date:
Create an Agile Project Charter in Smartsheet

## Project Plan
Agile Project Plan
Project Name | Online retailer
Project Manager | Ng Ka Ming, Liu Wai Man
Project Deliverable | Interactive website
Scope Statement | Other files can be uploaded to the website
Start Date | 1/24/2018
End Date | 3/14/2018
Overall Progress | 12%
Task Name | Responsible | Start | End | Days | Status
Sprint 1 | All member | 2018-01-24 | 2018-02-15 | 22 | Complete
Defining the scope | All member | 2018-01-24 | 2018-01-31 | 7 | Complete
Project planning | All member | 2018-01-31 | 2018-02-06 | 6 | Complete
Work distribution | Liu Wai Man | 2018-02-06 | 2018-02-08 | 2 | Complete
Sprint 2 | All member | 2018-02-08 | 2018-02-20 | 12 | Complete
Research | All member | 2018-02-08 | 2018-02-16 | 8 | Complete
System analysis | Some members | 2018-02-12 | 2018-02-18 | 6 | Complete
Logical design | Some members | 2018-02-16 | 2018-02-20 | 4 | Complete
Sprint 3 | All member | 2018-02-20 | 2018-03-14 | 22 | Complete
Database design | Some members | 2018-02-20 | 2018-02-25 | 5 | Complete
Implementation | Some members | 2018-02-25 | 2018-03-11 | 14 | Complete
Testing | Some members | 2018-03-11 | 2018-03-14 | 3 | Complete
Create an Agile Project Plan in Smartsheet

## User Story
Agile User Story Template
User Story ID | As a <type of user> | I want to <perform some task> | so that I can <achieve some goal>
1 | As an online retailer | I want to order product from supplier | so that I have product to sell on the website
2 | As a logistic | I want to know the shipping address of online retailer | so that I can transport product to online retailer warehouse
3 | As an employee | I want to confirm the ordered products are shipped to the warehouse | so that I can update the database of the product storage
4 | As a customer | I want to select product from the website | so that I can buy the product
5 | As a customer | I want to select product details (e.g. size, color, etc.) | so that I have more choices of the product.
6 | As I customer | I want to select product quantity | so that I can buy more same product at the same time
7 | As a customer | I want to select a shipping address | so that I can decide which address to receive the product
8 | As I customer | I want to select shipping speed (e.g. 5 days) | so that I can receive the product within the period
9 | As a customer | I want to select payment method | so that I have to pay for the product
10 | As an online retailer | I want to select related customer product shipping detailes from database | so that I can notify the logistics provider
11 | As a logistic | I want to receive product shipping details from online retailer | so that I can transport the product to customer address
Track Agile User Stories in Smartsheet

## Product Backlog
Agile Product Backlog
Task Name | Story | Sprint Ready | Priority | Status | Story Points | Assigned to Sprint
Sprint 1 | Yes | Yes | High | Not complete | 48 | Yes
Online retailer order product from supplier | Yes | Yes | High | Complete | 32 | Yes
Logistic transport product to online retailer warehouse | Yes | Yes | High | Not Started | 8 | Yes
Employee confirm the product | Yes | Yes | Low | Not Started | 8 | Yes
Sprint 2 | Yes | Yes | High | Not Started | 95 | Yes
Customer selects one of the products from the website | Yes | Yes | High | Not Started | 20 | Yes
Customer selects product details (size, color, etc.) | Yes | Yes | High | Not Started | 45 | Yes
Customer selects product quantity | Yes | Yes | Medium | Not Started | 30 | Yes
Sprint 3 | Yes | Yes | Medium | Not Started | 45 | Yes
Customer selects a shipping address | Yes | Yes | Medium | Not Started | 15 | Yes
Customer selects shipping option (logistics company) | Yes | Yes | Medium | Not Started | 25 | Yes
Customer selects payment method | Yes | Yes | Low | Not Started | 5 | Yes
Sprint 4 | Yes | Yes | Medium | Not Started | 64 | Yes
Logistics receives product shipping details from online retailer | Yes | Yes | Low | Not Started | 32 | Yes
Task 11 | No | No | Low | Not Started | 32 | No
Task 12 | No | No | Medium | Not Started | 0 | No
Sprint 5 | No | No | Low | Not Started | 64 | No
Task 13 | No | No | Low | Not Started | 48 | No
Task 14 | No | No | Low | Not Started | 8 | No
Task 15 | No | No | Low | Not Started | 8 | No
Create a Product Backlog in Smartsheet

## Sprint Backlog
Sprint Backlog Template ( Remaining outstanding efforts in hours )
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
User Story #1 | 8 | Project manager | Complete
Online retailer order product from supplier | 32 | All member | Complete | 7 | 5 | 3 | 2 | 2 | 2 | 2
Logistic transport product to online retailer warehouse | 16 | All member | Complete | 3 | 2 | 2 | 1 | 1 | 1 | 0
Employee confirm the product | 4 | Liu Wai Man | Complete | 4 | 3 | 2 | 2 | 2 | 2 | 2
Customer selects one of the products from the website | 8 | All member | Complete | 9 | 7 | 5 | 3 | 3 | 1 | 0
User Story #2 | 1 | Employee | Complete
Customer selects product details (size, color, etc.) | 2 | All member | Complete
Customer selects product quantity | 4 | Some members | Complete
Customer selects a shipping address | 5 | Some members | Complete
Customer selects shipping option (logistics company) | 7 | Some members | Complete
User Story #3 | 5 | Customer | Complete
Customer selects payment method | 6 | Some members | Complete
Logistics receives product shipping details from online retailer | 5 | Some members | Complete
Task
Task
User Story #4 | 8
Task
Task
Task
Task
User Story #5 | 3
Task
Task
Task
Task
Total |  |  |  | 23 | 17 | 12 | 8 | 8 | 6 | 4
S

## Test Plan
Agile Test Plan
Project Name | Online Retailer Website |  | Browser: | Firefox
Test Case ID | 1003 |  | Version: | 58.0.2
Written By: | Ng Ka Ming, Liu Wai Man |  | Description: | Online Retailer Website Testing
Tested By: | LAU CHUN HANG, Fong Cheuk Lok |  | Tested On: | 2018-02-14
Test # | Date | Action | Expected Results | Actual Results | Pass?
1 | 2018-02-14 | Logging in | Should get to home screen | User directed to different page | ✓
2 | 2018-02-16 | Signing up error | Finished registration have the 'Registration Completed' message | User finished registration website show the blank page. | ✓
3 | 2018-02-20 | Setting products information | Quantity in stock will decrease automatically when customer bought a product | Only show 'In Stock' | ✓
4 | 2018-02-23 | Making order | Customers can insert their own address | Customers can insert their own address | ✓
5 | 2018-02-27 | Choosing the logistic method | Provide scroll down list for customers choosing the logistic method | Provide checkbox for customers choosing the delivery efficency | ✓
6 | 2018-03-07 | Generating the .json file for supplier team | Supplier team can get our in stock quantity from the .json file | Supplier team can get our in stock quantity from the .json file | ✓
Create a Test Plan in Smartsheet

## Release Plan
Agile Release Plan
Sprint | Task | Start | End | Duration | Status | Release Date | Goal
1 | Drafting Service Blueprint | 2018-01-24 | 2018-01-31 | 7 | Released | 2016-02-12
1 | Collect the user requirement | 2018-01-24 | 2018-02-07 | 14 | Released | 2016-02-24
1 | Designing the databse structure | 2018-01-24 | 2018-02-07 | 14 | Released | 2016-03-01
2 | Designing and developing the online retailer website | 2018-02-07 | 2018-02-21 | 14 | Released | 2016-03-08
2 | Implementing the database | 2018-02-07 | 2018-02-21 | 14 | Released
2 | Imporving the online retailer website | 2018-02-07 | 2018-02-21 | 14 | Released
3 | Testing website errors | 2018-02-21 | 2018-03-07 | 14 | Released
3 | Debugging | 2018-02-21 | 2018-03-07 | 14 | Released
3 | Doing the document report and PowerPoint for presentation | 2018-02-21 | 2018-03-15 | 22 | On-going
3 | Recording presentation video | 2018-03-12 | 2018-03-15 | 3 | Released
0
0
0
0
0
0
0
0
0
Create an Agile Release Plan in Smartsheet